## Sheet1
E-Giant Market Place - Sophisticated portal for B2B and B2C
No | Feature Name | Screen No | Sprint | UI Team | Functional Team | Other Areas | Mgmt Man Hours | Senior Man Hours | Junior Man Hours | Remarks , if any
1 | Finalissing the Frame Work |  | 0 |  |  | Y | 16 hrs
2 | Resource Pooling |  | 0 | 2 | 4 | Y | 24 Hrs |  |  | Architect role, UI Prgmer & API Prgmers Etc
3 | Basic Design |  | 0 |  |  | Y | 40 Hrs | 100 Hrs
4 | Proposal to Client |  | 0 |  |  | Y | 24 Hrs
5 | Schedule for In house Team |  | 0 |  |  | Y | 16 Hrs
6 | Templates Selection |  | 0 | Y |  |  |  | 4 Hrs
7 | UI Color Codes |  | 1 | Y |  |  |  | 4Hrs
8 | Home Page | 30+ | 1 | Y | Y |  |  | 4 Hrs
8a | tradeshows
8ab | tradeshow page | 1
8ab1 | top tabs [all,today,this week,recent three months,from to to date,top events,online events,add event,share,more(top of home page)] | 11
8c | filter conditions on left side | 1
8c1 | filter condition applying on screen | 1(subitems -8)
8d | adiitional performance(Ex : promote event,carrer at times) | 1
8e | related search | 1
8f | homepage(inside of tradeshows) | 1(12)
8b | conferences(differnet page) | 1
8c | workshops(same as conferences page we can use) | 1
8d | virtual exops | 1
8e | webinars | 1
8f | online events (different page) | 1
8f1 | live webinars(7)(view more button,differnet page) | 1
8f2 | Watch Recorded Events(view more,differnet page) | 1
8f3 | Featured Events (view more button,differnet page) | 1
8f4 | Trending Keywords(8 tabs and different pages all) | 1
8f5 | Get Started with a Free Webinar(differnet page) | 1
8f6 | Events From
8f7 | Education & Training(different page, 6 tabs) | 1
8f8 | IT & Technology(different page, 6 tabs) | 1
8f9 | Medical & Pharma(different page, 6 tabs) | 1
8f10 | Banking & Finance(different page, 6 tabs | 1
8f11 | Business Services(different page, 6 tabs) | 1
8f12 | Wellness, Health & Fitness (different page, 6 tabs) | 1
8f13 | Science & Research(different page, 6 tabs) | 1
8x
8y
8z
8Aa
8A+A37b+A23
8Ac
8Ad